## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Iteration 1 | Iteration 1 | US-01 | As a student, I want to register and log in so that I can securely access the examination. | MUST HAVE | None | Priyanka G | 3- Completed
Iteration 1 | Iteration 1 | US-02 | As a student, I want to start and complete an examination session so that my exam attempt is recorded. | MUST HAVE | US-01 | Priyanka G | 3- Completed
Iteration 2 | Iteration 2 | US-03 | As an invigilator, I want the system to monitor face presence and detect multiple faces so that examination monitoring events can be recorded. | MUST HAVE | US-02 | Priyanka G | 3- Completed
Iteration 2 | Iteration 2 | US-04 | As an invigilator, I want browser tab-switch events to be detected and logged so that unusual examination activity can be reviewed. | MUST HAVE | US-02 | Priyanka G | 3- Completed
Iteration 3 | Iteration 3 | US-05 | As an invigilator, I want recorded monitoring events to be converted into an integrity score using predefined rules so that student behavior can be summarized numerically. | MUST HAVE | US-03, US-04 | Priyanka G | 3- Completed
Iteration 3 | Iteration 3 | US-06 | As an invigilator, I want students to be classified into Low Risk, Medium Risk, or High Risk based on predefined integrity-score thresholds so that examination behavior can be categorized for review. | MUST HAVE | US-05 | Priyanka G | 3- Completed
Iteration 4 | Iteration 4 | US-07 | As an invigilator, I want student behavioral data to be analyzed using K-Means and PCA so that behavioral patterns across students can be identified and visualized. | SHOULD HAVE | US-06 | Priyanka G | 3- Completed
Iteration 4 | Iteration 4 | US-08 | As an invigilator, I want an AI-assisted integrity report generated from recorded examination data so that monitoring information can be reviewed in a clear natural-language format. | SHOULD HAVE | US-05, US-06 | Priyanka G | 3- Completed
Iteration 5 | Iteration 5 | US-09 | As an invigilator, I want a dashboard displaying student risk levels, integrity scores, suspicious events, and analytics so that I can review examination results. | MUST HAVE | US-06, US-07, US-08 | Priyanka G | 3- Completed
Iteration 5 | Iteration 5 | US-10 | As an invigilator, I want an interactive analytics dashboard showing risk profiles, integrity scores, behavioral events, and analytical visualizations so that student performance can be reviewed efficiently. | MUST HAVE | US-07, US-09 | Priyanka G | 3- Completed
Iteration 5 | Iteration 5 | US-11 | As an invigilator, I want to export examination and monitoring data in CSV and JSON formats so that the results can be downloaded and reviewed outside the application. | SHOULD HAVE | US-09, US-10 | Priyanka G | 3- Completed
Iteration 5 | Iteration 5 | US-12 | As a developer, I want to perform end-to-end testing of the examination, monitoring, scoring, analytics, reporting, and export modules so that the system functions correctly as an integrated platform. | MUST HAVE | US-03, US-04, US-05, US-06, US-07, US-08, US-09, US-10, US-11 | Priyanka G | 3- Completed
Note on F1: ====== ID#AAACHV7b0aE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAACHV7b0aI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAACHV7b0ZY Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAACHV7b0Z8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAACHV7b0aM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAACHV7b0Zc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAACHV7b0Zg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAACHV7b0aQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAACHV7b0Zw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAACHV7b0ZQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAACHV7b0Z4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAACHV7b0Z0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAACHV7b0Zo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAACHV7b0Zk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAACHV7b0ZM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAACHV7b0Zs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAACHV7b0aA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAACHV7b0ZU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7