## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Priyanka G | 2026-09-09 | K-Means analysis failed with a NameError because the PCA visualization referenced an undefined risk_labels variable. | Sprint 4 | Priyanka G | Logical | Updated the PCA visualization to use the Risk_Level column directly instead of the undefined risk_labels variable. | 2026-09-09 | Closed | K-Means analysis and PCA visualization executed successfully after the fix.
2 | Priyanka G | 2026-09-15 | Gemini API generation failed because the initially configured model was not available for the API request. | Sprint 4 | Priyanka G | Logical | Verified the available Gemini model and updated the LangChain configuration to use gemini-3.6-flash. | 2026-09-15 | Closed | AI report generation was successfully tested after updating the model configuration.
3 | Priyanka G | 2026-09-17 | Complete Session JSON export contained NaN values for missing data, resulting in invalid JSON format. | Sprint 4 | Priyanka G | Logical | Handled missing Pandas values before JSON generation and converted them to None so they are exported as valid JSON null values. | 2026-09-17 | Closed | Complete Session JSON was validated successfully after the fix.
4 | Priyanka G | 2026-09-13 | Screenshot evidence capture caused the examination monitoring interface to freeze during webcam monitoring. | Sprint 4 | Priyanka G | Logical | Screenshot evidence capture was disabled/deferred to maintain stable webcam monitoring and examination functionality. | 2026-09-13 | Open | Screenshot evidence capture is planned for future implementation after resolving the monitoring stability issue.
5 | Priyanka G | 2026-09-18 | Gemini API requests returned a 429 RESOURCE_EXHAUSTED error after the available API quota was exceeded. | Sprint 4 | Priyanka G | Logical | Verified the API quota limitation and avoided repeated API calls during testing. Existing generated AI reports were retained for dashboard and export validation. | 2026-09-18 | Open | Further AI generation depends on API quota availability.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others